## Slide 1
This project has received funding from the European Union’s Horizon 2020 research and innovation Programme under grant agreement 945263 (IMMERSE)
WP8 Dissemination and Exploitation
Jeroen Weermeijer (WP Lead)
KU Leuven
EC Evaluation December 1st

## Slide 2
This project has received funding from the European Union’s Horizon 2020 research and innovation Programme under grant agreement 945263 (IMMERSE)
WP8 – OBJECTIVE
Seek out and valorize intellectual property (IP) generated during the project, and disseminating the objectives, approaches and research findings of this project to stakeholders and academics. Additionally, WP8 also aims to design fitting exploitation and sustainability plans, as well as provides prediction models for the future implementation of DMMH and other mHealth approaches in mental health.

## Slide 3
This project has received funding from the European Union’s Horizon 2020 research and innovation Programme under grant agreement 945263 (IMMERSE)
WP8 – Overview of tasks
Task 8.1. Set-up Exploitation Steering Group
Task 8.2. Dissemination plan
Task 8.3. Scientific exploitation plan
Task 8.4. Commercial exploitation plan
Task 8.5 Predictive models of implementation of digital mobile mental health technology

## Slide 4
This project has received funding from the European Union’s Horizon 2020 research and innovation Programme under grant agreement 945263 (IMMERSE)
WP8 – Task 8.1 Set-up Exploitation Steering Group
What?
Set-up of and orchestrating activities of an Exploitation Steering Group [ESG]
Prerequisite for Task 8.2, 8.3 and 8.4
When?
Set-up in month 4
With whom?
WP2 [Movisens]

## Slide 5
This project has received funding from the European Union’s Horizon 2020 research and innovation Programme under grant agreement 945263 (IMMERSE)
WP8 – Task 8.1 Exploitation Steering Group
Current status
  An ESG charter has been set-up delineating tasks of the ESG
ESG TASKS
Protection of intellectual property rights (IPR)
  Open innovation outputs [research output]
  Proprietary Assets [source-code of software]
Tracking of intellectual property developed throughout the project
  Linked to task 8.2
Development of exploitation pathways
  Linked to task 8.3 and 8.4

## Slide 6
This project has received funding from the European Union’s Horizon 2020 research and innovation Programme under grant agreement 945263 (IMMERSE)
WP8 – Task 8.1 Exploitation Steering Group
ESG, formal members
Inez Myin-Germeys (WP1); Martine van Nierop (WP1); Simon Krause (WP2); Joerg Ottenbacher (WP2); Thomas Ganslandt (WP3); Georgia Koppe (WP4); Luca Marelli (WP6); Ulrich Reininghaus (WP7); Anton Heretik (WP7); Iveta Nagyova (WP7); Matthias Schwannauer (WP7); Jeroen Weermeijer (WP8)
ESG, informal members: LRD representative

## Slide 7
This project has received funding from the European Union’s Horizon 2020 research and innovation Programme under grant agreement 945263 (IMMERSE)
WP8 – Overview of tasks
Task 8.1. Exploitation Steering Group
Task 8.2. Dissemination plan
Task 8.3. Scientific exploitation plan
Task 8.4. Commercial exploitation plan
Task 8.5 Predictive models of implementation of digital mobile mental health technology

## Slide 8
This project has received funding from the European Union’s Horizon 2020 research and innovation Programme under grant agreement 945263 (IMMERSE)
WP8 – Task 8.2 Dissemination plan
What?
  Plan for disseminating research outputs, deliverables and milestones of IMMERSE
  Delineates requirements for dissemination
When?
  Living document, continuously updated throughout the project
With whom?
  All WPs

## Slide 9
This project has received funding from the European Union’s Horizon 2020 research and innovation Programme under grant agreement 945263 (IMMERSE)
Current status:
A dissemination plan was set-up for the first 18 months of the project
Promised | Delivered?
1. Standard Acknowledgement | ✓
2. Procedures for planning articles, preregistrations and abstracts | ✓
3. Procedures for submitting articles (incl registered reports) | ✓
4. Post-review process | ✓
5. Open access (Grant Agreement, Article 29) | ✓
6. Setting up a Data Governance Board (DGB) | ✓
7. Outlining the topics of interest for the Early Career Researchers | ✓
8. Define principles of authorships | ✓
9. Setting up a dissemination tracking system | ✓
10. Create dissemination strategies for first 2 deliverables | X
WP8 – Task 8.2 Dissemination plan

## Slide 10
This project has received funding from the European Union’s Horizon 2020 research and innovation Programme under grant agreement 945263 (IMMERSE)
WP8 – Overview of tasks
Task 8.1. Exploitation Steering Group
Task 8.2. Dissemination plan
Task 8.3. Scientific exploitation plan
Task 8.4. Commercial exploitation plan
Task 8.5 Predictive models of implementation of digital mobile mental health technology

## Slide 11
This project has received funding from the European Union’s Horizon 2020 research and innovation Programme under grant agreement 945263 (IMMERSE)
WP8 – Task 8.3 Scientific exploitation plan
What?
  DROPS: a system for submitting abstracts to get data access
    Delineates who gets data access for planned study
    Archives what has been (or is being) done by whom
    Facilitates Open Science (e.g., pre-reg, timestamped dataset)
When?
  Living system, continuously updated throughout the project
With whom?
  WP1 and WP3

## Slide 12
This project has received funding from the European Union’s Horizon 2020 research and innovation Programme under grant agreement 945263 (IMMERSE)
WP8 – Task 8.3 Scientific exploitation plan
Current status:
DROPS has been developed
A data governance board has been set-up and decides on submitted abstracts
The board meets once a month
A short demo…

## Slide 13
NEXT SLIDE

## Slide 14
Abstract approved
1
3
2
Notify
Pre-reg
Data access & Follow-up

## Slide 15
This project has received funding from the European Union’s Horizon 2020 research and innovation Programme under grant agreement 945263 (IMMERSE)
WP8 – Task 8.3 Scientific exploitation plan
Current status:
Several abstract have been approved in our DROPS database

## Slide 16
This project has received funding from the European Union’s Horizon 2020 research and innovation Programme under grant agreement 945263 (IMMERSE)
WP8 – Overview of tasks
Task 8.1. Exploitation Steering Group
Task 8.2. Dissemination plan
Task 8.3. Scientific exploitation plan
Task 8.4. Commercial exploitation plan
Task 8.5 Predictive models of implementation of digital mobile mental health technology

## Slide 17
This project has received funding from the European Union’s Horizon 2020 research and innovation Programme under grant agreement 945263 (IMMERSE)
WP8 – Task 8.4 Commercial exploitation plan
What?
Identify commercial exploitation pathways
Implement market analysis and conduct business case for selected pathway
When?
Continuous throughout the duration of the project
With whom?
WP2 and WP7

## Slide 18
This project has received funding from the European Union’s Horizon 2020 research and innovation Programme under grant agreement 945263 (IMMERSE)
WP8 – Task 8.4 Commercial exploitation plan
Current status:
Commercial exploitation routes have been identified
  Exploitation routes independent of IMMERSE outcome [technology transfer package]
    Medical device regulation consultancy
    Therapy builder software [i.e., software package developed for creating interventions like DMMH]
    DROPS fee-for-service
  Exploitation routes dependent of IMMERSE outcome [WP8 aim]
    DMMH app exploitation as a mHealth product [e.g., reimbursement frameworks, HIBs]
      Preparatory: Explore maturation of previous proof-of-concept mHealth app to facilitate this process (if DMMH trial outcome is positive)

## Slide 19
This project has received funding from the European Union’s Horizon 2020 research and innovation Programme under grant agreement 945263 (IMMERSE)
WP8 – Overview of tasks
Task 8.1. Exploitation Steering Group
Task 8.2. Dissemination plan
Task 8.3. Scientific exploitation plan
Task 8.4. Commercial exploitation plan
Task 8.5 Predictive models of implementation of digital mobile mental health technology

## Slide 20
This project has received funding from the European Union’s Horizon 2020 research and innovation Programme under grant agreement 945263 (IMMERSE)
WP8 – Task 8.5 Predictive models of implementation of digital mobile mental health technology
What?
  Utilize data from the outcome of implementation studies (WP7) and stakeholder involvement (WP5) to construct predictive models of the adoption of the MoMent intervention by initial users, and how local policies and EU-wide regulations (WP6) influence other potential adopters
When?
  Month 36-48 of the project
With whom?
  WP5, WP6, WP7

## Slide 21
This project has received funding from the European Union’s Horizon 2020 research and innovation Programme under grant agreement 945263 (IMMERSE)
WP8 – Task 8.5 Predictive models of implementation of digital mobile mental health technology
Current status:
Not yet started – task for the future

## Slide 22
This project has received funding from the European Union’s Horizon 2020 research and innovation Programme under grant agreement 945263 (IMMERSE)
WP8 – Deliverables & Milestones
Milestone / deliverable | Title | Original deadline | Status
D8.1 | Exploitation Steering Committee Charter | Month 4 / 31.7.2021 | ✅
D8.2 | Dissemination plan | Month 6 / 30.9.2021 | ✅
D8.3 | Market analysis and strategy | Month 24 / 31.04.2023 | ongoing
D8.4 | White paper on forecasting models | Month 48 / 31.04.2025 | Not yet started
MS14 | Market for DMMH mapped | Month 24 / 31.04.2023 | ongoing

## Slide 23
This project has received funding from the European Union’s Horizon 2020 research and innovation Programme under grant agreement 945263 (IMMERSE)
WP8 – Challenges, delays, and solutions
Task 8.1. Set up Exploitation Steering Group
/
Task 8.2. Dissemination plan
Identify next dissemination goals -> continued collaborative effort
Task 8.3. Scientific exploitation plan
System imperfections -> no choice to differentiate between baseline and further data -> update
Task 8.4. Commercial exploitation plan
Developing a business case and market analysis may be challenging -> benefit from collaboration with a business school [e.g., Vlerick] or health economist
Task 8.5 Predictive models of implementation of digital mobile mental health technology
/

## Slide 24
This project has received funding from the European Union’s Horizon 2020 research and innovation Programme under grant agreement 945263 (IMMERSE)
WP8 – Dissemination
Dissemination tracker [WP1 collab] -> google doc
  Tracks: peer-reviewed publications, presentations, social media / websites, and press releases

## Slide 25
This project has received funding from the European Union’s Horizon 2020 research and innovation Programme under grant agreement 945263 (IMMERSE)
WP8 – Next steps
Task 8.1. Set up Exploitation Steering Group
Quarterly meetings
Task 8.2. Dissemination plan
Update dissemination plan for months 18-36
Task 8.3. Scientific exploitation plan
New iteration of DROPS based on user feedback [e.g., UX database]
Task 8.4. Commercial exploitation plan
Discuss exploitation options during next ESG [15/12/2022]
Develop business case and market analysis
Collab with health economist / business school
Task 8.5 Predictive models of implementation of digital mobile mental health technology
Literature review / business forecasting course / consult with health economists

## Slide 26
This project has received funding from the European Union’s Horizon 2020 research and innovation Programme under grant agreement 945263 (IMMERSE)
WP8 – End
Thank you for listening, questions?